## Approval Report mould release
|  | Trial out report |  |  |  | T1
Trial out date |  | 2026-01-09
KTK Mould Number |  | WZ-1278
cavity |  | 1
Part name |  | ABDECKUNG LI
Part number |  | 11732
incetion machine |  | 160T
clampiong force |  | 160T
screw Ø |  | 50mm
Material name |  | >PC+ABS< Pulse GX50 (nature)+ batch 4% color atlas grau
Material color |  | Black
mould temperature core |  | 49.9
mould temperature cavity |  | 49.9
centering Ø |  | Dia 99.8
mould length |  | 294
width |  | 350
hight |  | 350
CHECKLIST for MOULD apprval and release
1. | mould achivement |  | i. O. | n. i. O.
1.1 | Tool Indent Number
1.2 | Customer mould plates
1.3 | Fixing rings on both sides
1.4 | Lift bar _ red painted
1.5 | threads for handling in each plate
1.6 | all edges with champers
1.7 | disassembly notches existing
1.8 | tool functional plan lable on mould
1.9 | insulation plates are existing
1.10 | nozzle radius as requested
1.11 | electical switch for ejetor plate protecting
1.12 | hot runner connector existing
1.13 | lable for hot runner
1.14 | fine centering in the inserts
1.15 | greas grooves on all moveable parts
1.16 | all movable parts smoothly running
1.17 | all disassembling parts are marked
1.18 | part marking complete
1.19 | coling connectors according to KTKmould spec
1.20 | marked cooling circuit
1.21 | lable for cooling cycles existing
1.22 | cooling cycles are seal
1.23 | tool in according fo general security standards
1.24 | no plopping or smacking during open-close of mould
2. | Prozess Assesement
2.1 | machine setting as requested ( last mould tiral) |  | √
2.2 | injection machine size profortional related to part |  | √
2.3 | cycte time actually and as requesed |  | √
2.4 | venting areas ensure smoothly prozess |  | √
2.5 | part demolding: free falling |  | √
2.6 | no runner jumping |  | √
2.7 | perfect demolding of the parts and runner |  | √
2.8 | perfect filling |  | √
2.9 | startup without problemsn |  | √
2.10 | hot runner temperature stable |  | √
2.11 | mould temerature stable |  | √
2.12 | mould have no leakage |  | √
2.13 | fitting test successfully ( picture) |  | √
3. | Qualitäts Assesement (by ey )
3.1 | there are any sink marks |  | √
3.2 | flash or overmoulding areas |  | √
3.3 | part complete filled |  | √
3.4 | surface accoring the KTK spezifiactions |  | √
3.5 | is there any bending or warpage |  | √
3.6 | the tear off point on the gate is o.k |  | √
3.7 | there are visible filling flow- or weldlines |  | √
3.8 | can the part quality produced constant |  | √
3.9 | the actual part quality same as last trial out? |  | √
PROBLEMS during mould approval
| problem |  | needed actions and responsibility
4.1
4.2
4.3
4.4
4.5
5. | Final agreement Comany Concord / KTK / KK
MOULD APPROVED _ FREE FOR SHIPMENT The marked open points was discussed with all responsible peoples and will be finished before shipment |  |  |  |  | Date and Sign Company
Date and Sign Company KTK Mouldtec
Date and Sign Company
Note on B20: Tool achievement 模具成就（mu ju cheng jiu）
Note on M20: o.k. Xing (行)
Note on O20: not o.k. Bu xing (不行)
Note on B45: Process Assessment 过程评估 guo cheng ping gu
Note on B59: Quality Assessment 产品质量判断（视觉） chan pin zhi liang pan duan(shi jue)
Note on A69: Others qi ta de (其他的)

## actual water flow rate
| water flow rate / request 8-10 L/min | [5 empty] | request | 8 | to | 10 | L/min
colling line | actual rate |  | min. differnece |  | corrective action needed | description of correctivce action | [5 empty] | there is a formular inside ==> when you add the flow rate it will be working automatically
1 | 7.6 | l/min |  | l/min | NEEDED
2 | 8.1 | l/min |  | l/min | NEEDED
3 | 8.3 | l/min |  | l/min | NEEDED
4 | 6.2 | l/min |  | l/min | NEEDED
5 |  | l/min |  | l/min
6 |  | l/min |  | l/min
7 |  | l/min |  | l/min
8 |  | l/min |  | l/min
9 |  | l/min |  | l/min
10 |  | l/min |  | l/min
11 |  | l/min |  | l/min
12 |  | l/min |  | l/min
13 |  | l/min |  | l/min
14 |  | l/min |  | l/min
15 |  | l/min |  | l/min
16 |  | l/min |  | l/min
17 |  | l/min |  | l/min
18 |  | l/min |  | l/min
19 |  | l/min |  | l/min
20 |  | l/min |  | l/min
21 |  | l/min |  | l/min
22 |  | l/min |  | l/min
23 |  | l/min |  | l/min
24 |  | l/min |  | l/min
25 |  | l/min |  | l/min
26 |  | l/min |  | l/min
27 |  | l/min |  | l/min
28 |  | l/min |  | l/min
29 |  | l/min |  | l/min
30 |  | l/min |  | l/min
31 |  | l/min |  | l/min
32 |  | l/min |  | l/min
33 |  | l/min |  | l/min
34 |  | l/min |  | l/min
35 |  | l/min |  | l/min
36 |  | l/min |  | l/min
37 |  | l/min |  | l/min
38 |  | l/min |  | l/min

## Thermo pictures _set up
Thermo pictures of mould / set up
CAVITY
Thermo pictures of mould / set up
CORE

## Thermo pictures after 60 min
Thermo pictures of mould / after 60 min
CAVITY
Thermo pictures of mould / after 60 min
CORE

## Process details
Injection process details of mould release
shot weight
22.74
Part name |  | ABDECKUNG LI | [6 empty] | part weight
Part number (Customer) |  | 11732 | [6 empty] | 16.9
used injection machine size |  | 160T | [6 empty] | runner weight
Ø of screw |  | 50mm | [5 empty] | mm | 5.84
required rough material |  | >PC+ABS< Pulse GX50 (nature)+ batch 4% color atlas grau
color of rough material |  | Nature | [6 empty] | needed clampong force
Date of release trial |  | 10-1-2026 | [6 empty] | 160T
cavity |  | 1+1
|  | HZ 1 | HZ 2 | HZ 3 | HZ 4 | HZ 5 | HZ 6 | HZ 7 | HZ 8 | HZ 9 | HZ 10
cylinder temperatures | °C | 1+1 HZ 1: 230; 1+1 HZ 2: 230; 1+1 HZ 3: 230; 1+1 HZ 4: 225; 1+1 HZ 5: 215
cylinder temperatures | °C
hot runner temperatures | °C
hot runner temperatures | °C
mould tem core side | °C | 1+1 HZ 1: 80
mould tem cavity side | °C | 1+1 HZ 1: 80
injection pressure | bar | 1+1 HZ 1: 120; 1+1 HZ 2: 100
holding pressure | bar | 1+1 HZ 1: 80
| s | 1+1 HZ 1: 4
switch over posittion | mm | 1+1 HZ 1: 45; 1+1 HZ 2: 43
back pressure | bar | 1+1 HZ 1: 15
injection profile | % | 1+1 HZ 1: 55; 1+1 HZ 2: 25; 1+1 HZ 8: Speed in %
| mm | 1+1 HZ 1: 42; 1+1 HZ 2: 30; 1+1 HZ 8: Start of Injection
dosing way | mm | 1+1 HZ 1: 51; 1+1 HZ 2: Darstellung der Werte:
suck back | mm | 5 |  | HZ 1 | HZ 2 | HZ 3 | HZ 4 | HZ 5…
melt cushion | mm | 1+1 HZ 1: 43
injection time | s | 5 |  | p/v… | p/v5 | p/v4 | p/v3 | p/v2 | p/v1
holding time | s | 1+1 HZ 1: 4
cooling time | s | 20 |  | t1 | t2 | t3 | t4 | t5 | t6 | t7
cycle time | s | 60
mold set up time | min
400
400
400
400
400
400
400
400
0 mm
Schneckenweg
Zeit
X mm
mm
0 s
Note on A4: DRS-Ident-No. DRS 模号（DRS mu hao）
Note on J4: Shotweight 总重（zong zhong）
Note on A5: Name 产品名(chan pin ming)
Note on A6: Cavities 模穴数(mu xue shu)
Note on J6: Weight of the parts 产品重量 （chan pin zong zhong)
Note on A7: Project 项目（xiang mu）
Note on A8: Used machine size - name 使用的机台型号，名字 (shi yong de ji tai xing hao, ming zi)
Note on J8: Weight of the runner 水口重量（shui kou zhong liang）
Note on A9: Ø of the screw 螺杆直径(luo gan zhi jing)
Note on A10: required rough material 胶料(jiao liao)
Note on A11: color of rough material 胶料颜色(jiao liao yan se)
Note on J11: needed clamping force 需要的锁模力（Xūyào de suǒ mó lì）
Note on A12: Date 日期(ri qi)
Note on A13: Revisor 修订者(xiu ding zhe)
Note on A15: Cylinder temperatures 炮筒温度(pao tong wen du)
Note on A16: Cylinder temperatures 炮筒温度 (pao tong wen du)
Note on A17: Hotrunner temperatures 热流道温度 (re liu dao wen du)
Note on A18: Hotrunner temperatures 热流道温度 (re liu dao wen du)
Note on A19: Tool temperatures Coreside - inside the tool 后模实际模温 (hou mu shi ji mu wen)
Note on A20: Tool temperatures Cavity side - inside the tool 前模实际模温 (qian mu shi ji mu wen)
Note on A21: Injection pressure 注射压力 (zhu she ya li)
Note on A22: Holding pressure 保压(bao ya)
Note on A24: Switch over position 保压转换位置 (bao ya zhuan huan wei zhi)
Note on A25: Back pressure 背压(bei ya)
Note on A26: Injection profile 射胶段(she jiao duan)
Note on A28: Dosing way 射胶行程(she jiao xing cheng)
Note on L28: Description of the setting values
Note on A29: Suck back 抽胶松退(chou jiao song tui)
Note on A30: Melt cushion - position end of holding pressure 溶胶缓冲- 保压终点位置 (rong jiao huan chong-bao ya zhong dian wei zhi)
Note on A31: Injection time 射胶时间(she jiao shi jian)
Note on A32: Holding time 保压时间(bao ya shi jian)
Note on A33: Cooling time 冷却时间(leng que shi jian)
Note on A34: Cycle time 周期(zhou qi)

## filling study+pictures of parts
HZ 1

## actual mould pictures
actual mould pictures
Operator side
Moving half
Fixed half
Non-Operator side

## Open issues
actual mould pictures
Issue : Flash