## Approval Report mould release
|  | Trial out report |  |  |  | T1
Trial out date |  | 2025-03-19
KTK Mould Number |  | WZ-1226
cavity |  | 1
Part name |  | UNTERLAGE POL KENZ ECE BASIS/MACAU / HK PHEV (BEV/NEV)
Part number |  | 5A8D972
incetion machine |  | Hai Tian SA800 800T
clampiong force |  | 800T
screw Ø |  | 90
Material name |  | PP Finalloy EBP-1415 KA001
Material color |  | black
mould temperature core |  | 25
mould temperature cavity |  | 25
centering Ø |  | Ø159.8+0.1
mould length |  | 906
width |  | 690
hight |  | 897
CHECKLIST for MOULD apprval and release
1. | mould achivement |  | i. O. | n. i. O.
1.1 | Tool Indent Number
1.2 | Customer mould plates
1.3 | Fixing rings on both sides
1.4 | Lift bar _ red painted
1.5 | threads for handling in each plate
1.6 | all edges with champers
1.7 | disassembly notches existing
1.8 | tool functional plan lable on mould
1.9 | insulation plates are existing
1.10 | nozzle radius as requested
1.11 | electical switch for ejetor plate protecting
1.12 | hot runner connector existing
1.13 | lable for hot runner
1.14 | fine centering in the inserts
1.15 | greas grooves on all moveable parts
1.16 | all movable parts smoothly running
1.17 | all disassembling parts are marked
1.18 | part marking complete
1.19 | coling connectors according to KTKmould spec
1.20 | marked cooling circuit
1.21 | lable for cooling cycles existing
1.22 | cooling cycles are seal
1.23 | tool in according fo general security standards
1.24 | no plopping or smacking during open-close of mould
2. | Prozess Assesement
2.1 | machine setting as requested ( last mould tiral)
2.2 | injection machine size profortional related to part
2.3 | cycte time actually and as requesed
2.4 | venting areas ensure smoothly prozess
2.5 | part demolding: free falling
2.6 | no runner jumping
2.7 | perfect demolding of the parts and runner
2.8 | perfect filling
2.9 | startup without problemsn
2.10 | hot runner temperature stable
2.11 | mould temerature stable
2.12 | mould have no leakage
2.13 | fitting test successfully ( picture)
3. | Qualitäts Assesement (by ey )
3.1 | there are any sink marks
3.2 | flash or overmoulding areas
3.3 | part complete filled
3.4 | surface accoring the KTK spezifiactions
3.5 | is there any bending or warpage
3.6 | the tear off point on the gate is o.k
3.7 | there are visible filling flow- or weldlines
3.8 | can the part quality produced constant
3.9 | the actual part quality same as last trial out?
PROBLEMS during mould approval
| problem |  | needed actions and responsibility
4.1
4.2
4.3
4.4
4.5
5. | Final agreement Comany Concord / KTK / KK
MOULD APPROVED _ FREE FOR SHIPMENT The marked open points was discussed with all responsible peoples and will be finished before shipment |  |  |  |  | Date and Sign Company
Date and Sign Company KTK Mouldtec
Date and Sign Company
Note on B20: Tool achievement 模具成就（mu ju cheng jiu）
Note on M20: o.k. Xing (行)
Note on O20: not o.k. Bu xing (不行)
Note on B45: Process Assessment 过程评估 guo cheng ping gu
Note on B59: Quality Assessment 产品质量判断（视觉） chan pin zhi liang pan duan(shi jue)
Note on A69: Others qi ta de (其他的)

## cooling cycles
cooling cycle scheme
CAVITY
cooling cycle scheme
CORE

## actual water flow rate
| water flow rate / request 8-10 L/min | [5 empty] | request | 8 | to | 10 | L/min
colling line | actual rate |  | min. differnece |  | corrective action needed | description of correctivce action | [5 empty] | there is a formular inside ==> when you add the flow rate it will be working automatically
1 | 7.5 | l/min | 8 | l/min | NEEDED
2 | 7.5 | l/min | 8 | l/min | NEEDED
3 | 8 | l/min | 8 | l/min | NEEDED
4 | 8 | l/min | 8 | l/min | NEEDED
5 | 8 | l/min | 8 | l/min | NEEDED
6 | 8 | l/min | 8 | l/min | NEEDED
7 | 8 | l/min | 8 | l/min | NEEDED
8 | 8 | l/min | 8 | l/min | NEEDED
9 | 7 | l/min | 8 | l/min | NEEDED
10 | 7 | l/min | 8 | l/min | NEEDED
11 | 7.5 | l/min | 8 | l/min | NEEDED
12 | 7.5 | l/min | 8 | l/min | NEEDED
13 | 7 | l/min | 1 | l/min | NEEDED
14 | 7 | l/min | 1 | l/min | NEEDED
15 | 7 | l/min | 1 | l/min | NEEDED
16 | 7 | l/min | 1 | l/min | NEEDED
17 | 8 | l/min |  | l/min
18 |  | l/min | 8 | l/min | NEEDED
19 |  | l/min | 8 | l/min | NEEDED
20 |  | l/min |  | l/min | NEEDED
21 |  | l/min |  | l/min | NEEDED
22 |  | l/min |  | l/min | NEEDED
23 |  | l/min |  | l/min | NEEDED
24 |  | l/min |  | l/min | NEEDED
25 |  | l/min |  | l/min | NEEDED
26 |  | l/min |  | l/min | NEEDED
27 |  | l/min |  | l/min | NEEDED
28 |  | l/min |  | l/min | NEEDED
29 |  | l/min |  | l/min | NEEDED
30 |  | l/min |  | l/min | NEEDED
31 |  | l/min |  | l/min | NEEDED
32 |  | l/min |  | l/min | NEEDED
33 |  | l/min |  | l/min | NEEDED
34 |  | l/min |  | l/min | NEEDED
35 |  | l/min |  | l/min | NEEDED
36 |  | l/min |  | l/min | NEEDED
37 |  | l/min |  | l/min | NEEDED
38 |  | l/min |  | l/min | NEEDED

## Thermo pictures _set up
Thermo pictures of mould / set up
CAVITY
Thermo pictures of mould / set up
CORE

## Thermo pictures after 60 min
Thermo pictures of mould / after 60 min
Core
Thermo pictures of mould / after 60 min
Cavity

## Process details
Injection process details of mould release
shot weight
|  | WZ-1226 | [6 empty] | 353.52g
Part name |  | UNTERLAGE POL KENZ ECE BASIS/MACAU / HK PHEV (BEV/NEV) | [6 empty] | part weight
Part number (Customer) |  | 5A8D972 | [6 empty] | 351.22g
used injection machine size |  | Hai Tian SA800 800T | [6 empty] | runner weight
Ø of screw |  | 90 | [5 empty] | mm | g
required rough material |  | PP Finalloy EBP-1415 KA001
color of rough material |  | black | [6 empty] | needed clampong force
Date of release trial |  | 2025-03-19
cavity |  | 1
|  | HZ 1 | HZ 2 | HZ 3 | HZ 4 | HZ 5 | HZ 6 | HZ 7 | HZ 8 | HZ 9 | HZ 10
cylinder temperatures | °C | 1 HZ 1: 230; 1 HZ 2: 225; 1 HZ 3: 220; 1 HZ 4: 215; 1 HZ 5: 210
cylinder temperatures | °C
hot runner temperatures | °C | 1 HZ 1: 230; 1 HZ 2: 230; 1 HZ 3: 230; 1 HZ 4: 230
hot runner temperatures | °C
mould tem core side | °C | 1 HZ 1: 35
mould tem cavity side | °C | 1 HZ 1: 35
injection pressure | bar | 1 HZ 1: 900
holding pressure | bar | 1 HZ 1: 350
| s | 1 HZ 1: 8
switch over posittion | mm | 1 HZ 1: 31
back pressure | bar | 1 HZ 1: 30; 1 HZ 2: 50
injection profile | % | 1 HZ 1: 40; 1 HZ 8: Speed in %
| mm | 1 HZ 1: 31; 1 HZ 8: Start of Injection
dosing way | mm | 1 HZ 1: 90; 1 HZ 2: Darstellung der Werte:
suck back | mm | 4 |  | HZ 1 | HZ 2 | HZ 3 | HZ 4 | HZ 5…
melt cushion | mm | 1 HZ 1: 23.5
injection time | s | 1.68 |  | p/v… | p/v5 | p/v4 | p/v3 | p/v2 | p/v1
holding time | s | 1 HZ 1: 8
cooling time | s | 13 |  | t1 | t2 | t3 | t4 | t5 | t6 | t7
cycle time | s | 43.3
mold set up time | min
400
400
400
400
400
400
400
400
0 mm
Schneckenweg
Zeit
X mm
mm
0 s
Note on A4: DRS-Ident-No. DRS 模号（DRS mu hao）
Note on J4: Shotweight 总重（zong zhong）
Note on A5: Name 产品名(chan pin ming)
Note on A6: Cavities 模穴数(mu xue shu)
Note on J6: Weight of the parts 产品重量 （chan pin zong zhong)
Note on A7: Project 项目（xiang mu）
Note on A8: Used machine size - name 使用的机台型号，名字 (shi yong de ji tai xing hao, ming zi)
Note on J8: Weight of the runner 水口重量（shui kou zhong liang）
Note on A9: Ø of the screw 螺杆直径(luo gan zhi jing)
Note on A10: required rough material 胶料(jiao liao)
Note on A11: color of rough material 胶料颜色(jiao liao yan se)
Note on J11: needed clamping force 需要的锁模力（Xūyào de suǒ mó lì）
Note on A12: Date 日期(ri qi)
Note on A13: Revisor 修订者(xiu ding zhe)
Note on A15: Cylinder temperatures 炮筒温度(pao tong wen du)
Note on A16: Cylinder temperatures 炮筒温度 (pao tong wen du)
Note on A17: Hotrunner temperatures 热流道温度 (re liu dao wen du)
Note on A18: Hotrunner temperatures 热流道温度 (re liu dao wen du)
Note on A19: Tool temperatures Coreside - inside the tool 后模实际模温 (hou mu shi ji mu wen)
Note on A20: Tool temperatures Cavity side - inside the tool 前模实际模温 (qian mu shi ji mu wen)
Note on A21: Injection pressure 注射压力 (zhu she ya li)
Note on A22: Holding pressure 保压(bao ya)
Note on A24: Switch over position 保压转换位置 (bao ya zhuan huan wei zhi)
Note on A25: Back pressure 背压(bei ya)
Note on A26: Injection profile 射胶段(she jiao duan)
Note on A28: Dosing way 射胶行程(she jiao xing cheng)
Note on L28: Description of the setting values
Note on A29: Suck back 抽胶松退(chou jiao song tui)
Note on A30: Melt cushion - position end of holding pressure 溶胶缓冲- 保压终点位置 (rong jiao huan chong-bao ya zhong dian wei zhi)
Note on A31: Injection time 射胶时间(she jiao shi jian)
Note on A32: Holding time 保压时间(bao ya shi jian)
Note on A33: Cooling time 冷却时间(leng que shi jian)
Note on A34: Cycle time 周期(zhou qi)

## filling study+pictures of parts
actual mould pictures
Holding pressure test
short shot

## actual mould pictures
actual mould pictures

## Fitting picture
actual mould pictures

## LOP_FOT T0
List of open points / LOP |  |  |  | STAGE | 1 | T1 | 2025-01-19
[5 empty] | 2 | T2 | 2025-03-19
[5 empty] | 3 | T3
4
5
6
7
Trial out in China / Status |  | Date | 2025-01-19 | actual part 3D file
part name |  | UNTERLAGE POL KENZ ECE BASIS/MACAU / HK PHEV (BEV/NEV)
part number |  | 5A8D972 |  | Injection TYPE
OEM Project |  | 2024-079 |  | mold will used as
Customer mould number |  | 2024-079_BMW G70 |  | cavities | 1
KTK-mould number |  | WZ-1226 |  | Material 1 | Z-0917-24
TOOL RESPONSIBLE/TRACKER |  |  |  | Material 2
TOOLMAKER |  | KTK-Mouldtec GmbH |  |  | request | current
Legende |  |  |  | part weight / gramm
Status |  |  |  | injection ma. clamping force
| OPEN / schdule or actions are critical |  |  | cycle time / seconds
IN WORK/corrective actions settled / need to realize and bring in
| done and succsessfully approved |  |  | Shot weight
TECHNICAL POINTS
No. | Photo |  | Problem description | planned corrective action | Status | Responsible | Target Date | Tryout Date | effectiveness checked / picture | addional action needed | OTHER NOTES
1 | 5A8D972 |  | The needle is too deep inside the part. 产品进胶点过低 | Adjusting the position of needle,only deep insde part by 0.5mm. 调整阀针，产品需调到0.5MM |  | Toolmaker |  |  | 进胶口阀针调整后有小批锋 | a few flash
2 | 5A8D972 |  | Scratches,EDM marks. 产品拉伤火花纹、段差 | Checking and polishing. 检查模具，重新省模修正 |  | Toolmaker |  |  | 一侧火花纹未加工到位 | still EDM mark
3 | 5A8D972 |  | Ejector pins scratched the ring. 两侧产品定位圈拉白 | Reduce the height of ring, in order to reduce the stress. 建议顶针定位圈减胶0.5MM修正 |  | Toolmaker |  |  |  | has been improved
4 | 5A8D972 |  | Flash披风 | Re-fitting 重新配模修正 |  | Toolmaker |  |  | 产品刮手 | still flash
5 | 5A8D972 |  | Scratch 刮伤 | Check the PL and polishing. 检查分型面是否有毛刺，省模。 |  | Toolmaker |  |  | 披锋 | still flash
6 |  |  | Fitting is not good. 局部红丹不到 | Re-fitting 重新配模修正 |  | Toolmaker |  |  |  | has been improved
7 |  |  | Fitting is too hard. 插烧 | Re-fitting 重新配模修正 |  | Toolmaker |  |  |  | has been improved
8 |  |  | Visible date clocks on the front side | Don’t make the clocks so deep. |  | Toolmaker |  |  |  | has been improved
9 |  |  | Cycle time | Check the cycle time. In reference list is 42s and in the MFA is 43s. You used the cycle time 55s. |  | Toolmaker |  |  | 43S
10 |  |  | Clamping force | Missing information about needed clamping force |  | Toolmaker |  |  | 300T
11 |  |  | AI | Rotate the AI stamp by current status. We will send the review with the actual numbers. |  | Toolmaker
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28